## Coverage
BMU COVERAGE PLAN
Coverage targets remain the sign-off goal, but functional sequences are intentionally right-sized. Representative directed cases and constrained-random traffic establish functionality; any remaining reachable bins are closed later with targeted Coverage Closure rather than by duplicating large exhaustive sweeps.
Risk colors: | HIGH | MEDIUM | STANDARD
Coverage ID | Type | What it verifies | Target / Bins | Sample on | Main stimulus | Risk
C-OP | Functional | 21 approved legal operation/CSR mode identifiers. Unsupported GREV modes are tracked separately in C-GREV. Legal NOP is tracked separately in C-NOP and does not count as one of the 21 legal modes. | 21 bins; operation/CSR tests. | Accepted legal request | All 18 operation sequences; csr_read; csr_write; mixed | STANDARD
C-A | Cross | Detailed operations x representative A classes; ensure broad operand-class coverage without duplicating exhaustive sweeps. | Functional sequences provide representative/random A coverage; any residual reachable A-class holes are closed later with targeted closure. | Accepted legal request | Operation sequences through MAX; targeted Coverage Closure for residual holes | STANDARD
C-LOG | Cross | Logic modes x important bit/boundary behavior. | Functional OR/ORN/XOR/XNOR scenarios use randomized traffic plus representative boundary/equal/complement cases; full residual bins, if any, are closure-only. | Accepted legal logic request | bmu_or_sequence; bmu_orn_sequence; bmu_xor_sequence; bmu_xnor_sequence; Coverage Closure as needed | STANDARD
C-MODE | Functional | Documented runtime mode changes: OR/ORN, XOR/XNOR, SLT/SLTU and CSR-WA/WB, both directions. | Explicit mode-pair bins; no generic zbb enable assumption. | Accepted legal request | bmu_or_sequence; bmu_orn_sequence; bmu_xor_sequence; bmu_xnor_sequence; bmu_slt_sequence; bmu_sltu_sequence; bmu_csr_write_sequence; bmu_mixed_sequence | STANDARD
C-SH | Cross | SRL/SRA/ROR shift/rotate amounts across positive/negative and boundary operand classes. | Functional sequences use constrained-random amounts plus explicit boundary/corner cases; remaining bins are closure-only. | Accepted legal request | bmu_srl_sequence; bmu_sra_sequence; bmu_ror_sequence; Coverage Closure as needed | MEDIUM
C-BIT | Cross | Representative one-hot bit movement for SRL/SRA/ROR; full onehot x amount matrix is a coverage target, not a functional-volume requirement. | Functional sequences exercise representative one-hot/boundary cases; missing reachable bins are closed later. | Accepted legal request | bmu_srl_sequence; bmu_sra_sequence; bmu_ror_sequence; Coverage Closure | MEDIUM
C-INV | Cross | BINV selected index and original target-bit value. | Functional sequence uses randomized traffic, explicit boundary indices, extremes and toggle-twice checks; residual index/value holes close later. | Accepted legal request | bmu_binv_sequence; Coverage Closure as needed | STANDARD
C-UP | Cross | Upper B bits must not affect low-mode/index selection for SRL/SRA/ROR/BINV/GREV. | Functional sequences use representative upper-B independence checks; full residual cross bins are closure-only. | Accepted/isolated request | bmu_srl_sequence; bmu_sra_sequence; bmu_ror_sequence; bmu_binv_sequence; bmu_grev_sequence; Coverage Closure | MEDIUM
C-AR | Functional | SUB borrow propagation/wrap and SH2ADD shift-out, wrap and carry propagation. | Representative boundary carry/borrow endpoints are tested functionally; additional bins are closed only if coverage shows a hole. | Accepted legal request | bmu_sh2add_sequence; bmu_sub_sequence | STANDARD
C-REL | Functional | SUB operand relation and equality/wrap behavior. | Equality and directed wrap/borrow scenarios establish behavior; no redundant relation sweep is required in the functional sequence. | Accepted legal request | bmu_sub_sequence | STANDARD
C-CMP | Cross | SLT/SLTU/MAX x sign-pair x operation-specific relation (<,=,>). | Functional tests cover random, equality and critical signed/unsigned boundaries; full reachable sign-pair x relation closure is deferred to project-level Coverage Closure. | Accepted legal request | bmu_sltu_sequence; bmu_slt_sequence; bmu_max_sequence; Coverage Closure | MEDIUM
C-CTZ | Functional | Expected trailing-zero count 0..32. | Functional CTZ uses directed corners plus 16 smart constrained-random count targets; missing count bins are closure-only after the CTZ bug is resolved. | Accepted legal request | bmu_ctz_sequence; Coverage Closure after bug fix | MEDIUM
C-CTZ-X | Cross | CTZ count x A[31] where reachable. | Functional CTZ randomizes higher bits above the first set bit; residual reachable count/sign bins are closed later after the CTZ bug is resolved. | Accepted legal request | bmu_ctz_sequence; Coverage Closure after bug fix | STANDARD
C-POP | Functional | Expected population count 0..32. | Functional CPOP uses directed patterns plus 16 target-weight constrained-random requests; remaining weight bins are closure-only after the CPOP bug is resolved. | Accepted legal request | bmu_cpop_sequence; Coverage Closure after bug fix | STANDARD
C-POP-X | Cross | Population weight x A[31] where reachable. | Functional tests use representative one-hot/one-cold and constrained-random weights; residual cross bins are deferred until after the CPOP bug is fixed. | Accepted legal request | bmu_cpop_sequence; Coverage Closure after bug fix | STANDARD
C-BYTE | Functional | SEXT.B low-byte functional classes and sign boundary. | Functional sequence covers explicit 00/01/7F/80/FE/FF corners plus constrained-random positive/negative bytes; exhaustive 256-byte closure is not required for functional execution. | Accepted legal request | bmu_sext_b_sequence; Coverage Closure only if residual bins are required | STANDARD
C-BYTE-X | Cross | SEXT.B low-byte behavior vs random upper-A bits. | Constrained-random upper-A values plus the explicit A[31] vs A[7] transition prove upper bits are ignored; residual bins are closure-only. | Accepted legal request | bmu_sext_b_sequence; Coverage Closure as needed | STANDARD
C-PACK | Cross | Six low-half classes in A x six in B; distinct source ordering. | 36 bins; PACK-02; additional asymmetric vector. | Accepted legal request | bmu_pack_sequence | STANDARD
C-PACK-B | Cross | Source lane A/B x bit index 0..15. | 32 propagation bins; PACK-03. | Accepted legal request | bmu_pack_sequence | STANDARD
C-GREV | Functional | All 32 low-five-bit modes; mode 24 legal, 31 isolated unsupported modes. | 32 bins; GREV-03. | Own predicates distinguish legal and unsupported GREV modes. | bmu_grev_sequence; bmu_errors_sequence | MEDIUM
C-GREV-B | Functional | Onehot position 0..31 with mode 24. | 32 bins; GREV-02. | Accepted legal request | bmu_grev_sequence | STANDARD
C-IGN | Functional | CTZ/CPOP/SEXT.B: B changes while relevant A is unchanged. PACK: upper halves change while low halves are fixed. | Representative paired requests prove ignored-input behavior without sweeping every value. | Accepted legal request | bmu_ctz_sequence; bmu_cpop_sequence; bmu_sext_b_sequence; bmu_pack_sequence | STANDARD
C-CSR / C-CSR-B | Cross | Three source paths x 8 selected-source classes; three paths x 32 onehot bits. | 24 selected-source class bins plus 96 onehot propagation bins; CSR-01/03/04 and CSR-06. | Accepted legal request | bmu_csr_read_sequence; bmu_csr_write_sequence; bmu_mixed_sequence | MEDIUM
C-NOP | Functional | Legal no-operation request: valid_in=1, ap='0 and csr_ren_in=0. A previous nonzero result must not leak through. | One legal NOP bin plus prior-result-nonzero observation; NOP-01. | Accepted legal NOP request | bmu_smoke_sequence; bmu_reference_model_unit_test | HIGH
C-NEG | Cross | Recipe x single forbidden-field/CSR-conflict reason x valid_in 0/1; missing-required-control cases remain separate and blocked until defined. | Size derives from the Illegal Control Matrix. Known invalid controls must be exercised with valid_in=0 and 1. | Observed known-negative controls. error value is independent of valid_in; result_ff update/hold follows valid_in. Q2 only exact error-cycle alignment. | bmu_errors_sequence; bmu_random_sequence | HIGH
C-RST | Cross | 21 modes x valid_in 0/1 under reset; startup/midstream, reset-over-error and recovery flags. | 42 cross bins plus startup, midstream, reset-over-error and recovery observations. | Active reset edge | bmu_reset_sequence; bmu_random_sequence | HIGH
C-HOLD | Cross | 8 families x hold-length class 1, 2, 3-7, 8+. | 32 bins; execute TST-05 for all families. | Cycles with valid_in=0; family is taken from the last accepted request. | bmu_valid_in_sequence; bmu_random_sequence | MEDIUM
C-VALID | Cross | 8 families x valid transition 00, 01, 10, 11. | 32 bins; TST-06. | Every non-reset cycle | bmu_valid_in_sequence | MEDIUM
C-TR | Cross | All ordered 21 x 21 legal mode pairs on adjacent accepted cycles. | 441 bins; TST-07. Track conflict-recovery separately. | Adjacent accepted legal cycles | bmu_orn_sequence; bmu_xnor_sequence; bmu_srl_sequence; bmu_binv_sequence; bmu_sltu_sequence; bmu_sext_b_sequence; bmu_grev_sequence; bmu_csr_write_sequence; bmu_errors_sequence; bmu_mixed_sequence; bmu_smoke_sequence | STANDARD
C-REC | Functional | Known conflict reason x valid at conflict (0/1) x subsequent legal recovery observed. | Define per approved guard list; TST-08 supplies legal-conflict-legal runs. | Separate temporal coverage; do not use C-TR, whose history clears on conflict. error value is known for confirmed conflicts; Q2 only exact error-cycle alignment. | bmu_errors_sequence | STANDARD
C-LAT | Functional | Accepted request in cycle N x observed matching result in cycle N+1; include adjacent accepted requests, legal NOP and final drain. | All 21 legal modes plus NOP represented; TST-02 and NOP-01 prove alignment, and TST-11 checks drain/accounting. | Sample accepted requests and compare only to the explicitly one-cycle-delayed expected-result queue. | bmu_smoke_sequence; all legal operation/CSR sequences; bmu_mixed_sequence | HIGH
C-ERR-V | Cross | Request legality class x valid_in 0/1 x observed error; include legal modes, legal NOP, known illegal control conflict, CSR conflict and unsupported GREV non-error class. | All defined reachable combinations. error must not be gated by valid_in. | Sample expected legality/error independently from result-register enable. Q2, if open, affects exact cycle alignment only. | bmu_errors_sequence; bmu_valid_in_sequence; bmu_reset_sequence; bmu_grev_sequence; bmu_random_sequence | HIGH
CODE | Code / Check | Line, branch, condition/expression and toggle coverage on actual DUT hierarchy. | Initial line/branch >=95% subject to approval; other holes reviewed. | Simulator instrumentation; per-build reports; justified exclusions only. | All runnable tests | STANDARD
ASSERT | Code / Check | Reset priority, hold, aligned update, legal NOP zero update, scan setup and known controls. | Define properties for resolved behavior; review antecedent hits and vacuity. | Implement assertions/checkers. Result latency is confirmed; Q2 gates only error-cycle-specific properties. | reset; valid_in; smoke; errors; mixed | HIGH

## Sequences
BMU SEQUENCE PLAN
One row per sequence/test. Scenario counts and states below reflect the right-sized functional plans agreed during implementation. Directed corner cases and limited constrained-random stimulus are used for functionality; pure cross/bin closure is deferred when it would duplicate functional intent. Execution state is current through SEXT.B; MAX is not yet run.
Risk colors: | HIGH | MEDIUM | STANDARD
Sequence | Test | Category | Responsibility / Legal Recipe | Scenarios | Risk | State
bmu_or_sequence | bmu_or_test | Operation | Control recipe: ap.lor=1. Expected value: A ¦ B. | 3 | STANDARD | Implemented / PASS (29/29 valid)
bmu_orn_sequence | bmu_orn_test | Operation | Control recipe: ap.lor=1, ap.zbb=1. Expected value: A ¦ ~B. | 4 | STANDARD | Implemented / PASS (42/42 valid)
bmu_xor_sequence | bmu_xor_test | Operation | Control recipe: ap.lxor=1. Expected value: A ^ B. | 3 | STANDARD | Implemented / PASS (40/40 valid)
bmu_xnor_sequence | bmu_xnor_test | Operation | Control recipe: ap.lxor=1, ap.zbb=1. Expected value: ~(A ^ B). | 4 | STANDARD | Implemented / PASS (42/42 valid)
bmu_srl_sequence | bmu_srl_test | Operation | Control recipe: ap.srl=1. Expected value: unsigned(A) >> s. | 5 | MEDIUM | Implemented / PASS (54/54 valid)
bmu_sra_sequence | bmu_sra_test | Operation | Control recipe: ap.sra=1. Expected value: signed(A) >>> s. | 4 | MEDIUM | Implemented / PASS (43/43 valid)
bmu_ror_sequence | bmu_ror_test | Operation | Control recipe: ap.ror=1. Expected value: rotate_right_32(A, s). | 5 | MEDIUM | Implemented / PASS (44/44 valid)
bmu_binv_sequence | bmu_binv_test | Operation | Control recipe: ap.binv=1. Expected value: A ^ (32-bit one << s). | 5 | MEDIUM | Implemented / PASS (36/36 valid)
bmu_sh2add_sequence | bmu_sh2add_test | Operation | Control recipe: ap.sh2add=1, ap.zba=1. Expected value: ((A << 2) + B) modulo 2^32. | 4 | STANDARD | Implemented / PASS (30/30 valid)
bmu_sub_sequence | bmu_sub_test | Operation | Control recipe: ap.sub=1; ap.zba=0. Expected value: (A-B) modulo 2^32. | 4 | STANDARD | Implemented / PASS (31/31 valid)
bmu_sltu_sequence | bmu_sltu_test | Operation | Control recipe: ap.slt=1, ap.sub=1, ap.unsign=1. Expected value: unsigned(A)<unsigned(B) ? 1 : 0. | 5 | MEDIUM | Functional PASS (32/32 valid); closure deferred
bmu_slt_sequence | bmu_slt_test | Operation | Control recipe: ap.slt=1, ap.sub=1; ap.unsign=0. Expected value: signed(A)<signed(B) ? 1 : 0. | 5 | MEDIUM | Functional PASS (30/30 valid); closure deferred
bmu_ctz_sequence | bmu_ctz_test | Operation | Control recipe: ap.ctz=1. Expected value: trailing-zero count of A, with CTZ(0)=32. | 3 | MEDIUM | FAILED – Bug Reported (6/36 valid passed)
bmu_cpop_sequence | bmu_cpop_test | Operation | Control recipe: ap.cpop=1. Expected value: sum of all 32 operand bits. | 4 | STANDARD | FAILED – Bug Reported (15/56 valid passed)
bmu_sext_b_sequence | bmu_sext_b_test | Operation | Control recipe: ap.siext_b=1. Expected value: sign_extend_32(A[7:0]). | 4 | STANDARD | Implemented / PASS (30/30 valid)
bmu_max_sequence | bmu_max_test | Operation | Control recipe: ap.max=1, ap.sub=1; ap.unsign=0. Expected value: larger signed operand. | 5 | MEDIUM | Planned; MAX-05 deferred to Coverage Closure
bmu_pack_sequence | bmu_pack_test | Operation | Control recipe: ap.pack=1. Expected value: {B[15:0], A[15:0]}. | 5 | STANDARD | Planned
bmu_grev_sequence | bmu_grev_test | Operation | Control recipe: ap.grev=1; B[4:0]=24 for REV8. Expected value: {A[7:0], A[15:8], A[23:16], A[31:24]}. | 5 | MEDIUM | Planned
bmu_csr_read_sequence | bmu_csr_read_test | Shared / smoke | CSR read path; shared CSR-06 bit sweep. | 3 | MEDIUM | Planned
bmu_csr_write_sequence | bmu_csr_write_test | Shared / smoke | CSR write-A/write-B paths; execute write portions of shared CSR-06. | 3 | MEDIUM | Planned
bmu_errors_sequence | bmu_errors_test | Shared / smoke | Reviewed invalid controls, CSR conflicts, error/recovery and known-negative directed cases. Legal NOP is owned by the smoke sequence. | 12 | HIGH | Planned; 4 blocked
bmu_reset_sequence | bmu_reset_test | Shared / smoke | Synchronous reset, priority and mid-traffic recovery. | 4 | HIGH | Planned
bmu_valid_in_sequence | bmu_valid_in_test | Shared / smoke | Hold lengths, valid transitions, repeated updates and CSR hold. | 4 | HIGH | Planned
bmu_mixed_sequence | bmu_mixed_test | Shared / smoke | Deterministic adjacent-mode and CSR path transitions only; no random campaigns. | 2 | MEDIUM | Planned
bmu_random_sequence | bmu_random_test | Campaign | Limited constrained-random campaigns only: fixed seeds, bounded trials, supplemental coverage and targeted hole filling. | 5 | HIGH | Planned
bmu_smoke_sequence | bmu_smoke_test | Shared / smoke | Bring-up, reset, OR/XOR/NOP one-cycle alignment, explicit NOP zeroing, drain and scan setup. | 4 | HIGH | Implemented / PASS
Model qualification (no DUT sequence) | bmu_reference_model_unit_test | Support | Known-answer checks for the independent reference model, including legal NOP, before DUT sign-off. | 7 | MEDIUM | Implemented / PASS

## Scenarios
BMU SCENARIO PLAN
Scenarios are grouped under their owning sequence. Each scenario has a distinct verification objective; redundant cases are merged or removed. Functional sequences use directed corner/boundary cases plus limited constrained-random stimulus. Full cross/bin closure is deferred to project-level Coverage Closure when it would otherwise duplicate functional intent. Status and evidence below reflect executed results through SEXT.B; MAX is planned but not yet run.
Risk colors: | HIGH | MEDIUM | STANDARD
bmu_or_sequence ¦ bmu_or_test ¦ 3 scenarios ¦ Group risk: STANDARD
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Result / Evidence
OR-01 | Operation | Generate 16 legal randomized A/B pairs. | Compare the complete 32-bit OR result (A ¦ B). | C-OP, C-A | STANDARD | Passed | 16/16 randomized requests passed.
OR-02 | Operation | Apply 5 directed adjacent/boundary A/B pairs spanning low-bit, byte/halfword edges and the MSB. | Selected OR bits combine correctly with no neighboring-bit corruption. | C-LOG | STANDARD | Passed | 5/5 directed boundary requests passed.
OR-03 | Operation | Use 4 representative A patterns; for each apply B=00000000 and B=FFFFFFFF. 8 requests. | F=A for B=0; F=FFFFFFFF for B=FFFFFFFF. | C-A | STANDARD | Passed | 8/8 representative requests passed.
bmu_orn_sequence ¦ bmu_orn_test ¦ 4 scenarios ¦ Group risk: STANDARD
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Result / Evidence
ORN-01 | Operation | Generate 16 legal randomized A/B pairs. | Compare the full 32-bit OR-with-inverted-B result (A ¦ ~B). | C-OP, C-A | STANDARD | Passed | 16/16 randomized requests passed.
ORN-02 | Operation | Apply 8 representative directed A/B patterns covering zero, all-one and asymmetric operand classes. | Representative operand classes produce the expected A ¦ ~B value. | C-A | STANDARD | Passed | 8/8 representative requests passed.
ORN-03 | Operation | Apply 16 directed boundary-bit cases across bit/byte/halfword/MSB positions. | Bit inversion and OR behavior remain correct across boundary positions. | C-LOG | STANDARD | Passed | 16/16 boundary requests passed.
ORN-04 | Operation | Run ORN and OR on the same asymmetric operands on adjacent valid cycles. 2 requests. | Only the documented zbb mode changes the result; cycle alignment remains correct. | C-MODE, C-TR | STANDARD | Passed | 2/2 mode-transition requests passed.
bmu_xor_sequence ¦ bmu_xor_test ¦ 3 scenarios ¦ Group risk: STANDARD
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Result / Evidence
XOR-01 | Operation | Generate 16 legal randomized A/B pairs. | Compare the full 32-bit XOR result. | C-OP, C-A | STANDARD | Passed | 16/16 randomized requests passed.
XOR-02 | Operation | Use 4 representative A values; for each apply B=A and B=~A. 8 requests. | F=00000000 for equal operands and F=FFFFFFFF for complements. | C-A | STANDARD | Passed | 8/8 equal/complement requests passed.
XOR-03 | Operation | Apply 16 directed boundary-position cases with B=0 or B=FFFFFFFF. | F=A or ~A as applicable across low-bit, byte/halfword and MSB boundaries. | C-LOG | STANDARD | Passed | 16/16 boundary requests passed.
bmu_xnor_sequence ¦ bmu_xnor_test ¦ 4 scenarios ¦ Group risk: STANDARD
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Result / Evidence
XNOR-01 | Operation | Generate 16 legal randomized A/B pairs. | Compare the full 32-bit XNOR result. | C-OP, C-A | STANDARD | Passed | 16/16 randomized requests passed.
XNOR-02 | Operation | Use 4 representative A values; for each apply B=A and B=~A. 8 requests. | F=FFFFFFFF for equal operands and F=00000000 for complements. | C-A | STANDARD | Passed | 8/8 equal/complement requests passed.
XNOR-03 | Operation | Apply 16 directed boundary-position cases with B=0 or B=FFFFFFFF. | F=~A or A as applicable across low-bit, byte/halfword and MSB boundaries. | C-LOG | STANDARD | Passed | 16/16 boundary requests passed.
XNOR-04 | Operation | Run XOR/XNOR mode transition on identical asymmetric operands. 2 requests. | Correct result and one-cycle alignment for the documented zbb mode switch. | C-MODE, C-TR | STANDARD | Passed | 2/2 mode-transition requests passed.
bmu_srl_sequence ¦ bmu_srl_test ¦ 5 scenarios ¦ Group risk: MEDIUM
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Result / Evidence
SRL-01 | Operation | Generate 16 constrained-random A/B requests with varied shift amounts B[4:0]. | Logical right shift with zero fill; s=0 preserves A. | C-SH, C-A | MEDIUM | Passed | 16/16 randomized requests passed.
SRL-02 | Operation | Use one-hot A positions k={0,7,8,15,16,23,24,31}; apply 3 representative shifts per position. 24 requests. | The one-hot bit moves to k-s when k>=s; otherwise the result becomes zero. | C-BIT | MEDIUM | Passed | 24/24 one-hot boundary requests passed.
SRL-03 | Operation | A=80000001 with shifts s={0,1,30,31}. 4 requests. | 80000001, 40000000, 00000002, 00000001 respectively. | C-SH | MEDIUM | Passed | 4/4 corner-shift requests passed.
SRL-04 | Operation | Use 4 representative (A,s) pairs, each repeated with two nonzero B[31:5] patterns. 8 requests. | Only B[4:0] affects the shift result; upper B bits are ignored. | C-UP | MEDIUM | Passed | 8/8 upper-B-independence requests passed.
SRL-05 | Operation | Apply SRL then SRA to A=80000000 with s=1. 2 requests. | SRL=40000000; SRA=C0000000 with correct mode/cycle alignment. | C-MODE, C-TR | MEDIUM | Passed | 2/2 SRL/SRA mode requests passed.
bmu_sra_sequence ¦ bmu_sra_test ¦ 4 scenarios ¦ Group risk: MEDIUM
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Result / Evidence
SRA-01 | Operation | Generate 16 constrained-random positive/negative A values with varied shift amounts. | Arithmetic right shift preserves sign and uses signed 32-bit A. | C-SH, C-A | MEDIUM | Passed | 16/16 randomized requests passed.
SRA-02 | Operation | Apply 11 representative one-hot/sign-boundary shift cases spanning low bits, byte/halfword boundaries and the MSB. | Shifted bit/sign behavior is correct at representative boundary positions. | C-BIT | MEDIUM | Passed | 11/11 representative one-hot requests passed.
SRA-03 | Operation | Apply 8 directed corner cases using positive/negative extrema and shifts including 0, 1 and 31. | Sign-fill and extreme-shift behavior match signed arithmetic-right-shift semantics. | C-SH | MEDIUM | Passed | 8/8 directed corner requests passed.
SRA-04 | Operation | Repeat representative A/shift cases with changed B[31:5]. 8 requests. | Only B[4:0] affects the shift amount; upper B bits are ignored. | C-UP | MEDIUM | Passed | 8/8 upper-B-independence requests passed.
bmu_ror_sequence ¦ bmu_ror_test ¦ 5 scenarios ¦ Group risk: MEDIUM
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Result / Evidence
ROR-01 | Operation | Generate 16 constrained-random A/B requests with varied rotate amounts. | Rotate-right behavior is correct for general legal inputs; s=0 returns A. | C-SH, C-A | MEDIUM | Passed | 16/16 randomized requests passed.
ROR-02 | Operation | Use one-hot A at k={0,7,8,15,16,23,24,31}; apply s=1 and s=31. 16 requests. | The one-hot bit appears at (k-s) modulo 32. | C-BIT | MEDIUM | Passed | 16/16 one-hot rotation requests passed.
ROR-03 | Operation | A=80000001 with s={0,1,31}. 3 requests. | 80000001, C0000000, 00000003 respectively. | C-SH | MEDIUM | Passed | 3/3 wrap/corner requests passed.
ROR-04 | Operation | Repeat representative rotate cases with changed B[31:5]. 4 requests. | Only B[4:0] selects the rotate amount; upper B bits are ignored. | C-UP | MEDIUM | Passed | 4/4 upper-B-independence requests passed.
ROR-05 | Operation | Apply 5 directed invariant/alternating-pattern rotate cases. | Zero/all-one invariants and alternating-pattern wrap behavior are preserved. | C-SH | MEDIUM | Passed | 5/5 invariant-pattern requests passed.
bmu_binv_sequence ¦ bmu_binv_test ¦ 5 scenarios ¦ Group risk: MEDIUM
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Result / Evidence
BINV-01 | Operation | Generate 16 constrained-random legal A/B requests. | Exactly the selected bit A[B[4:0]] toggles; all other bits remain unchanged. | C-INV, C-A | MEDIUM | Passed | 16/16 randomized requests passed.
BINV-02 | Operation | Apply 8 representative boundary bit indices spanning low, byte/halfword and MSB positions. | Boundary-index inversion toggles only the requested bit. | C-INV | MEDIUM | Passed | 8/8 boundary-index requests passed.
BINV-03 | Operation | A=00000000,index=31 and A=FFFFFFFF,index=0. 2 requests. | 80000000 and FFFFFFFE respectively. | C-INV | MEDIUM | Passed | 2/2 extreme requests passed.
BINV-04 | Operation | Repeat representative bit indices with changed B[31:5]. 8 requests. | Only B[4:0] selects the target bit; upper B bits are ignored. | C-UP | MEDIUM | Passed | 8/8 upper-B-independence requests passed.
BINV-05 | Operation | Invert the same selected bit twice using the first expected result as the second A. 2 requests. | The second inversion restores the original A; both results are checked independently. | C-INV, C-TR | MEDIUM | Passed | 2/2 toggle-twice requests passed.
bmu_sh2add_sequence ¦ bmu_sh2add_test ¦ 4 scenarios ¦ Group risk: STANDARD
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Result / Evidence
SH2-01 | Operation | Generate 16 legal constrained-random A/B pairs with ap.sh2add=1 and ap.zba=1. | F=((A<<2)+B) modulo 2^32. | C-OP, C-A | STANDARD | Passed | 16/16 randomized requests passed.
SH2-02 | Operation | Use A={00000001,40000001,80000001,C0000001} with B=00000003. 4 requests. | F=00000007 for all four; A[31:30] shift out and must not affect the low 32-bit result. | C-AR | STANDARD | Passed | 4/4 top-bit-shift-out requests passed.
SH2-03 | Operation | A=3FFFFFFF,B=00000004 and A=FFFFFFFF,B=FFFFFFFF. 2 requests. | 00000000 and FFFFFFFB respectively; modulo-32-bit wrap is legal. | C-AR | STANDARD | Passed | 2/2 wrap requests passed.
SH2-04 | Operation | For k={2,7,8,15,16,23,24,31}, use A=(1<<(k-2))-1 and B=4. 8 requests. | F=1<<k, exercising carry propagation to representative boundary positions. | C-AR | STANDARD | Passed | 8/8 carry-chain requests passed.
bmu_sub_sequence ¦ bmu_sub_test ¦ 4 scenarios ¦ Group risk: STANDARD
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Result / Evidence
SUB-01 | Operation | Generate 16 legal constrained-random A/B pairs with sub=1 and zba=0. | F=(A-B) modulo 2^32. | C-OP, C-A | STANDARD | Passed | 16/16 randomized requests passed.
SUB-02 | Operation | A=B for A={00000000,00000001,80000000,FFFFFFFF}. 4 requests. | F=00000000 for all equality cases. | C-REL | STANDARD | Passed | 4/4 equality requests passed.
SUB-03 | Operation | A=0,B=1; A=80000000,B=1; A=7FFFFFFF,B=FFFFFFFF. 3 requests. | FFFFFFFF; 7FFFFFFF; 80000000 respectively. | C-AR | STANDARD | Passed | 3/3 wrap/corner requests passed.
SUB-04 | Operation | For k={1,7,8,15,16,23,24,31}, use A=(1<<k), B=1. 8 requests. | F=(1<<k)-1, exercising borrow propagation across representative boundaries. | C-AR | STANDARD | Passed | 8/8 borrow-chain requests passed.
bmu_sltu_sequence ¦ bmu_sltu_test ¦ 5 scenarios ¦ Group risk: MEDIUM
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Result / Evidence
SLTU-01 | Operation | Generate 16 constrained-random unsigned A/B comparisons. | Result is 1 iff unsigned(A)<unsigned(B), otherwise 0. | C-CMP, C-A | MEDIUM | Passed | 16/16 constrained-random requests passed.
SLTU-02 | Operation | Apply 10 directed equality/adjacent unsigned-boundary cases around 0, 7FFFFFFF, 80000000 and FFFFFFFF. | Equality returns 0; adjacent pairs verify unsigned ordering at boundaries. | C-CMP | MEDIUM | Passed | 10/10 equality/boundary requests passed.
SLTU-03 | Operation | Apply FFFFFFFF vs 0, 0 vs FFFFFFFF, 80000000 vs 7FFFFFFF, and the reverse. 4 requests. | Expected unsigned results are 0,1,0,1 respectively. | C-CMP | MEDIUM | Passed | 4/4 unsigned trap requests passed.
SLTU-04 | Coverage Closure | Construct all reachable (A[31],B[31]) x unsigned relation (<,=,>) bins. | All reachable sign-pair x unsigned-relation bins must be hit with correct SLTU result. | C-CMP | MEDIUM | Deferred – Coverage Closure | Not executed in the functional sequence; reserved for project-level closure.
SLTU-05 | Operation | Use A=FFFFFFFF,B=00000000; run unsign=1 then unsign=0. 2 requests. | SLTU=0 followed by SLT=1 with correct mode transition. | C-MODE, C-TR | MEDIUM | Passed | 2/2 SLTU/SLT mode requests passed.
bmu_slt_sequence ¦ bmu_slt_test ¦ 5 scenarios ¦ Group risk: MEDIUM
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Result / Evidence
SLT-01 | Operation | Generate 16 constrained-random signed A/B comparisons. | Result is 1 iff signed(A)<signed(B), otherwise 0; upper 31 result bits remain zero. | C-CMP, C-A | MEDIUM | Passed | 16/16 constrained-random requests passed.
SLT-02 | Operation | Apply 10 directed equality/adjacent signed-boundary cases around -1, 0, MIN and MAX. | Equality returns 0; adjacent vectors verify signed ordering at critical boundaries. | C-CMP | MEDIUM | Passed | 10/10 equality/boundary requests passed.
SLT-03 | Operation | A=80000000,B=7FFFFFFF and reverse. 2 requests. | Expected results are 1 then 0 across the signed MIN/MAX boundary. | C-CMP | MEDIUM | Passed | 2/2 MIN/MAX requests passed.
SLT-04 | Coverage Closure | Construct all reachable (A[31],B[31]) x signed relation (<,=,>) bins. | All reachable sign-pair x signed-relation bins must be hit with correct SLT result. | C-CMP | MEDIUM | Deferred – Coverage Closure | Not executed in the functional sequence; reserved for project-level closure.
SLT-05 | Operation | A=FFFFFFFE,B=FFFFFFFF; then swap. 2 requests. | Expected results are 1 then 0, verifying comparison between two negative operands. | C-CMP | MEDIUM | Passed | 2/2 negative-vs-negative requests passed.
bmu_ctz_sequence ¦ bmu_ctz_test ¦ 3 scenarios ¦ Group risk: MEDIUM
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Result / Evidence
CTZ-01 | Operation | Apply A={00000000,00000001,FFFFFFFF,80000000}. 4 directed requests. | Expected CTZ results are 32,0,0,31. | C-CTZ | MEDIUM | Failed – Bug Reported | 2/4 passed; failures observed for A=00000001 and A=80000000.
CTZ-02 | Operation | Generate 16 constrained-random A values using selected target CTZ counts across 0..31; force A[k]=1 and all lower bits 0 while randomizing higher bits. | Result must equal the selected k; higher bits above the first set bit must not affect the count. | C-CTZ, C-CTZ-X, C-A | STANDARD | Failed – Bug Reported | 2/16 constrained-random requests passed; 14/16 returned incorrect CTZ results.
CTZ-03 | Operation | Use representative A values with known CTZ counts k={0,7,8,15,16,23,31} plus A=0; for each apply B=00000000 and FFFFFFFF. 16 requests. | CTZ must be unchanged when B changes; CTZ(0)=32. | C-IGN | STANDARD | Failed – Bug Reported | B-independence passed for all 8 A pairs, but 14/16 functional results failed (7/8 A classes).
bmu_cpop_sequence ¦ bmu_cpop_test ¦ 4 scenarios ¦ Group risk: STANDARD
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Result / Evidence
POP-01 | Operation | Apply A={00000000,00000001,80000000,FFFFFFFF,FFFF0000,0000FFFF,AAAAAAAA,55555555}. 8 directed requests. | Expected population counts are 0,1,1,32,16,16,16,16. | C-POP, C-A | STANDARD | Failed – Bug Reported | 3/8 requests passed; failures show upper-half set bits are not counted correctly.
POP-02 | Operation | Generate 16 constrained-random A values with selected target population counts distributed across low, middle and high weights. | Result must equal the selected population count, independent of set-bit positions. | C-POP, C-POP-X | STANDARD | Failed – Bug Reported | 0/16 constrained-random requests passed.
POP-03 | Operation | Apply one-hot and one-cold patterns at bit positions {0,7,8,15,16,23,24,31}. 16 requests. | One-hot inputs return 1; one-cold inputs return 31 regardless of bit position. | C-POP-X | STANDARD | Failed – Bug Reported | 4/16 requests passed; lower-half one-hot cases passed while upper-half cases exposed incorrect counting.
POP-04 | Operation | Use 8 representative A patterns spanning counts 0,1,8,16,24,31,32 and a mixed pattern; for each apply B=00000000 and FFFFFFFF. 16 requests. | Population count must remain unchanged when B changes. | C-IGN | STANDARD | Failed – Bug Reported | B-independence passed for all tested pairs; 8/16 functional requests passed and 8/16 failed.
bmu_sext_b_sequence ¦ bmu_sext_b_test ¦ 4 scenarios ¦ Group risk: STANDARD
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Result / Evidence
SEXT-01 | Operation | Apply low-byte corner cases 00,01,7F,80,FE,FF with A[31:8]=0. 6 directed requests. | 00000000,00000001,0000007F,FFFFFF80,FFFFFFFE,FFFFFFFF. | C-BYTE | STANDARD | Passed | 6/6 directed corner requests passed.
SEXT-02 | Operation | Generate 16 constrained-random A values: 8 with A[7]=0 and 8 with A[7]=1; randomize A[31:8]. | Result depends only on A[7:0]; positive bytes zero-extend and negative bytes sign-extend. | C-BYTE-X, C-A | STANDARD | Passed | 16/16 constrained-random requests passed.
SEXT-03 | Operation | Use low bytes 7F and 80; for each apply B=00000000, FFFFFFFF and AAAAAAAA. 6 requests. | 7F -> 0000007F and 80 -> FFFFFF80 regardless of B. | C-IGN | STANDARD | Passed | 6/6 B-independence requests passed.
SEXT-04 | Operation | Apply A=8000007F followed by A=00000080 on adjacent valid cycles. 2 requests. | Results are 0000007F then FFFFFF80; sign comes from A[7], not A[31]. | C-BYTE-X, C-TR | STANDARD | Passed | 2/2 adjacent-transition requests passed.
bmu_max_sequence ¦ bmu_max_test ¦ 5 scenarios ¦ Group risk: MEDIUM
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Result / Evidence
MAX-01 | Operation | Generate 16 constrained-random signed A/B pairs covering positive/positive, negative/negative and mixed-sign operands. | Return the larger operand using signed comparison; return the full selected 32-bit operand. | C-CMP, C-A | MEDIUM | Failed – Bug Reported | 0/16 constrained-random requests passed. For every non-equal signed pair, the DUT returned the smaller signed
MAX-02 | Operation | A=B for A={00000000,00000001,80000000,FFFFFFFF}. 4 requests. | Return the common input value for every equality case. | C-CMP | MEDIUM | Passed | 4/4 equality cases passed. A=B produces the expected common operand value.
MAX-03 | Operation | Apply 80000000 vs 7FFFFFFF and reverse; FFFFFFFF vs 00000000 and reverse. 4 requests. | Return 7FFFFFFF for the MIN/MAX pair and 00000000 for the -1/0 pair in both operand orders. | C-CMP | MEDIUM | Failed – Bug Reported | 0/4 mixed-sign boundary requests passed. The DUT consistently selected the smaller signed operand in both operand orders.
MAX-04 | Operation | A=FFFFFFFE,B=FFFFFFFF; then swap. 2 requests. | Return FFFFFFFF in both orders, verifying signed ordering between two negative operands. | C-CMP | MEDIUM | Failed – Bug Reported | 0/2 negative-versus-negative requests passed. The DUT returned -2 instead of -1 in both operand orders.
MAX-05 | Coverage Closure | Construct all reachable (A[31],B[31]) x signed relation (<,=,>) bins. | All reachable sign-pair x signed-relation bins must be hit with correct signed maximum selection. | C-CMP | MEDIUM | Deferred – Coverage Closure | Not executed in the functional sequence; reserved for project-level closure.
bmu_pack_sequence ¦ bmu_pack_test ¦ 5 scenarios ¦ Group risk: STANDARD
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Result / Evidence
PACK-01 | Operation | Apply 4 directed corner/asymmetric pairs including A=12345678, B=ABCDEF01, swapped operands, zero low halves, and all-one low-half case | Result is exactly {B[15:0], A[15:0]} for every pair. | C-PACK | STANDARD | Failed – Bug Reported | 2/4 directed requests passed.Asymmetric operand cases showed reversed halfword orderin
PACK-02 | Operation | Generate 8 constrained-random A/B pairs with different low-half values and varied operand patterns | Result must concatenate B[15:0] into bits [31:16] and A[15:0] into bits [15:0]. | C-PACK , C-A | STANDARD | Failed – Bug Reported | 0/8 constrained-random requests passed. All observed results showed the two 16-bit source lanes in reversed order.
PACK-03 | Operation | Walk one bit through all A[15:0], then all B[15:0], with the other operand zero | A low-half bit must appear in output [15:0]; B low-half bit must appear in output [31:16] | C-PACK-B | STANDARD | Failed – Bug Reported | 0/32 bit-propagation requests passed. A[15:0] propagated to result[31:16] and B[15:0] propagated to result[15:0], opposite to the specified mapping.
PACK-04 | Operation | Fixed low halves 1234/ABCD; each upper half sweeps 0, FFFF, AAAA (9 pairs). | Result remains ABCD1234 regardless of upper-half changes. | C-IGN | STANDARD | Failed – Bug Reported | 0/5 functional requests matched the specified PACK result. Upper-half independence passed, but the packed low-half lanes were reversed.
PACK-05 | Operation | 16 explicitly defined ordered V16 pairs covering all eight A classes and asymmetric low-half patterns. | Model concatenation for each pair; include A=FFFF0000, B=FFFF0000 -> zero. | C-A, C-PACK | STANDARD | Deferred – Coverage Closure
bmu_grev_sequence ¦ bmu_grev_test ¦ 5 scenarios ¦ Group risk: MEDIUM
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Result / Evidence
GREV-01 | Operation | Apply A=12345678, 80010204, 00000001 with B[4:0]=24. | 78563412/04020180/01000000. | C-GREV | MEDIUM | Failed – Bug Reported | 0/3 directed REV8 requests passed. For mode 24, observed DUT results were consistent with swapping the upper and lower 16-bit halfwords instead of reversing the four byte lanes.
GREV-02 | Operation | Sweep all 32 values of B[4:0] using asymmetric A=12345678. | Mode24 reverses; isolated other modes give F=0, error=0. | C-GREV | MEDIUM | Passed | 5/5 representative non-24 modes passed. Modes 0, 1, 23, 25, and 31 produced result=0 and error=0 as expected.
GREV-03 | Operation | Keep B[4:0]=24 and repeat with two different nonzero B[31:5] patterns. | Only B[4:0] selects the mode; combined scenarios close all three C-UP classes without repeating GREV-03. | C-UP | MEDIUM | Failed – Bug Reported | 0/2 requests matched the specified REV8 result. B[31:5] independence itself passed because changing the upper B bits did not change the observed result, but the mode-24 result remained functionally incorrect.
GREV-04 | Operation | Apply REV8 twice on adjacent valid requests using A=A1B2C3D4 followed by the independently calculated D4C3B2A1. | Restore original A; independently check both values. | C-TR, C-A | MEDIUM | Failed – Bug Reported | 0/2 back-to-back REV8 requests matched the expected byte-reversed values. One-cycle transaction alignment was correct, but both results exhibited the same incorrect halfword-swap behavior.
bmu_csr_read_sequence ¦ bmu_csr_read_test ¦ 3 scenarios ¦ Group risk: MEDIUM
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Result / Evidence
CSR-01 | CSR | pply directed csr_rddata_in values such as 00000000, FFFFFFFF, 80000001, 12345678, AAAAAAAA, and 55555555 with ap=0 and csr_ren_in=1. Keep A and B different from the read data | Each CSR value appears unchanged on result_ff one cycle later. A and B must not affect the result. error=0 | C-CSR | MEDIUM | Passed | 6/6 directed CSR read requests passed. result_ff matched csr_rddata_in exactly for all representative data patterns.
CSR-02 | CSR | Apply three different CSR read values in consecutive valid cycles: 11111111, 22222222, and 44444444. | The value accepted in cycle N appears in cycle N+1. Each result must correspond to the previous cycle’s CSR value, with no stale or same-cycle result. | C-CSR | MEDIUM | Passed | 3/3 consecutive CSR read requests passed with correct one-cycle alignment and preserved request order.
CSR-03 | CSR | First register DEADBEEF using a valid CSR read. Then set valid_in=0 and change csr_rddata_in to 01234567, then 89ABCDEF. | result_ff remains DEADBEEF during both invalid cycles. Changing the CSR input must not update the registered result while valid_in=0. | C-CSR-B | MEDIUM | Passed | : The valid read registered DEADBEEF correctly, and result_ff held DEADBEEF across both subsequent valid_in=0 cycles despite csr_rddata_in changing.
bmu_csr_write_sequence ¦ bmu_csr_write_test ¦ 3 scenarios ¦ Group risk: MEDIUM
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Result / Evidence
CSR-03 | CSR | Set ap='0, ap.csr_write=1, ap.csr_imm=0, csr_ren_in=0, and valid_in=1. Apply A={12345678, 00000000, FFFFFFFF, 00000001, 80000000}. Keep B different from A. | The selected A value appears unchanged on result_ff one cycle later. B must not affect the result. error=0. | C-CSR | MEDIUM | Failed – Bug Reported | 0/5 requests passed. With csr_imm=0, the DUT consistently selected B instead of the specified A source.
CSR-04 | CSR | Set ap='0, ap.csr_write=1, ap.csr_imm=1, csr_ren_in=0, and valid_in=1. Apply B={89ABCDEF, 00000000, FFFFFFFF, 00000001, 80000000}. Keep A different from B. | The selected B value appears unchanged on result_ff one cycle later. A must not affect the result. error=0. | C-CSR | MEDIUM | Failed – Bug Reported | 0/5 requests passed. With csr_imm=1, the DUT consistently selected A instead of the specified B source.
CSR-08 | CSR | Apply three consecutive valid writes while changing csr_imm: first 0, then 1, then 0. Use distinct A and B values every cycle | The result must follow the source selected in each request and appear one cycle later. No stale selection from the preceding cycle. | C-TR, C-CSR | MEDIUM | Failed – Bug Reported | 0/3 consecutive source-selection requests passed. The selected source followed the opposite csr_imm polarity on every cycle; one-cycle alignment remained correct.
CSR-09 | CSR | csr_ren_in=1 and csr_write=1, both csr_imm values. | Data priority and error undefined pending Q4. | Blocked Q4 | MEDIUM | Blocked | Q4
CSR-10 | CSR | csr_imm=1 with csr_write=0; test read inactive/active. | Ignored versus invalid behavior pending Q4. | Blocked Q4 | MEDIUM | Blocked | Q4
bmu_reset_sequence ¦ bmu_error_test ¦ 8 scenarios ¦ Group risk: HIGH
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Result / Evidence
NEG-02 | CSR conflict | For each documented operation requiring csr_ren_in=0, apply its complete legal control recipe, then assert csr_ren_in=1 with no additional forbidden fields. Use valid_in=1. | The CSR conflict alone is sufficient: error=1, and result_ff=0 is captured at N+1. | C-NEG | HIGH | Passed | All CSR-versus-operation conflict checks passed. Each conflict produced error=1 and result_ff=0 as expected; no NEG-02 mismatch was reported.
NEG-03 | Required qualifier | Compare legal sh2add=1, zba=1 with illegal sh2add=1, zba=0. Keep all unrelated controls clear. | Legal request produces the SH2ADD result. Missing zba produces error=1 and captures result_ff=0 at N+1. | C-NEG | HIGH | Passed | SH2ADD without zba was correctly treated as invalid, while the legal zba=1 case produced result_ff=0x00000043. All checks passed.
NEG-04 | Forbidden qualifier | Compare legal sub=1, zba=0 with illegal sub=1, zba=1. Keep all unrelated controls clear. | Legal request produces A-B. The illegal Zba combination produces error=1 and captures result_ff=0 at N+1. | C-NEG | HIGH | Passed | SUB with zba=1 was correctly treated as invalid, while the legal zba=0 case produced result_ff=0x0000001B. All checks passed.
NEG-05 | GREV conflict | Use legal REV8 mode with grev=1 and b_in[4:0]=24. Apply two separate conflicts: one representative forbidden ap.* field, then csr_ren_in=1. | Each isolated conflict produces error=1 and captures result_ff=0 at N+1. | C-NEG | HIGH | Failed – Bug Reported | One isolated GREV conflict passed, but the GREV plus forbidden ap-field conflict (ap=0x8020000000, b_in[4:0]=24) failed. Expected error=1 and result_ff=0; the DUT produced error=0 and result_ff=0x5678123C.
NEG-06 | GREV unsupported mode | With grev=1 and all unrelated controls clear, apply unsupported modes 0,1,23,25,31 using valid_in=1. Repeat one representative mode with valid_in=0. | Unsupported mode alone is not a control conflict: error=0. With valid_in=1, zero is captured at N+1. With valid_in=0, result_ff holds. | C-GREV, C-ERR-V | MEDIUM | Passed | All representative unsupported GREV modes passed. Modes 0, 1, 23, 25, and 31 produced result_ff=0 and error=0 as expected, including the representative valid_in=0 hold case.
NEG-07 | Error/valid interaction | Apply a legal request with valid_in=1, followed by a known conflict with valid_in=0, followed by another legal request with valid_in=1. | During the invalid cycle, error=1 even though valid_in=0, while result_ff holds its previous legal value. The following legal request updates normally at N+1. | C-GREV, C-ERR-V | HIGH | Failed – Bug Reported | The result_ff hold and later legal recovery passed. However, during the conflicting request with valid_in=0, error was expected to remain 1 but the DUT produced error=0.
NEG-08 | Reset priority | First apply a known conflict with rst_l=1 and confirm error=1. Keep the conflicting controls asserted, then apply synchronous reset with rst_l=0. | Reset overrides the active conflict: error=0 and result_ff=0. | C-RST, C-NEG | HIGH | Failed – Bug Reported | Reset cleared result_ff and error as expected. However, the preceding active conflict failed to assert error=1, so the complete reset-priority scenario failed due to the existing error-detection bug.
bmu_reset_sequence ¦ bmu_reset_test ¦ 2scenarios ¦ Group risk: HIGH
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Blocker
TST-01 | Timing / setup | Apply reset at startup, after a nonzero result, and during a known conflict. Test with valid_in=0 and 1. | At the reset edge, result_ff=0 and error=0. Normal operation resumes after reset release. | C-RST, C-ERR-V | HIGH | Passed | All startup-reset, post-nonzero-result, conflict-reset, and recovery checks passed. Reset correctly cleared result_ff and error, and normal operation resumed after reset release.
TST-02 | Timing / setup | Assert reset during back-to-back traffic while a result is pending. Release reset and send one legal request. | The pending result is discarded. Reset clears result_ff and error; the post-reset result appears one cycle later. | C-RST, C-LAT | HIGH | Passed | Reset during back-to-back traffic passed. result_ff was cleared to 0 on reset, no stale result was observed, and the post-reset CSR request completed correctly one cycle later.
bmu_valid_in_sequence ¦ bmu_valid_in_test ¦ 4 scenarios ¦ Group risk: HIGH
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Result / Evidence
TST-03 | Timing / valid control | Register a known nonzero result, then apply valid_in=0 for 1, 2, and 3 cycles while changing operands and control fields. Include one legal and one conflicting control case. | result_ff holds its previous value throughout the idle cycles. error continues to reflect the current control combination and is not gated by valid_in. | C-HOLD, C-ERR-V | HIGH | Passed | result_ff correctly held 11111111, 22222222, and 33333333 during 1-, 2-, and 3-cycle valid_in=0 intervals, despite operand changes.
TST-04 | Timing / valid control | Apply representative transitions 00, 01, 10, and 11 using legal requests from the main operation families. | A request updates result_ff one cycle later only when its sampled valid_in=1; otherwise, the previous result is retained. | C-VALID | MEDIUM | Passed | The valid_in transitions 00, 01, 11, and 10 behaved correctly. Valid requests updated result_ff one cycle later, while invalid cycles held the previous result.
bmu_smoke_sequence ¦ bmu_smoke_test ¦ 4 scenarios ¦ Group risk: HIGH
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Blocker
TST-02 | Smoke / timing | Apply adjacent valid OR, XOR, and NOP requests, then drive valid_in=0 to drain the final pending response. | Every request is observed exactly one cycle later in order, including the final request, with no dropped or repeated result. | C-LAT, C-TR | HIGH | Passed
NOP-01 | Control | Register a nonzero result, then apply valid_in=1, ap='0, and csr_ren_in=0. | Legal NOP produces error=0 and captures result_ff=0 one cycle later. | C-NOP, C-LAT, C-ERR-V | HIGH | Passed
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk
TST-07 | Timing / transition | Apply all 21 legal BMU/CSR modes once in a deterministic back-to-back order with valid_in=1. Follow them with a legal NOP and one legal operation, then apply one idle drain cycle. Use distinct operand values wherever possible. | Each accepted request produces its expected result exactly one cycle later and in order. No result is dropped, repeated, or selected from the previous operation path. NOP produces zero, and the following legal operation updates normally. | C-TR, C-LAT, C-OP, C-CSR, C-NOP | HIGH
Model qualification (no DUT sequence) ¦ bmu_reference_model_unit_test (support) ¦ 7 scenarios ¦ Group risk: MEDIUM
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Blocker
RV-01 | Model qualification | CPOP(FFFF0000), CPOP(80000000), CPOP(FFFFFFFF). | 16, 1, 32 respectively. | Model only | MEDIUM | Passed
RV-02 | Model qualification | CTZ(0), CTZ(1), CTZ(00000008), CTZ(80000000). | 32, 0, 3, 31 respectively. | Model only | MEDIUM | Passed
RV-03 | Model qualification | REV8(12345678), mode=24; ROR(80000001, 1). | 78563412; C0000000. | Model only | MEDIUM | Passed
RV-04 | Model qualification | SLT/SLTU with A=FFFFFFFF, B=0; MAX with same operands. | SLT=1; SLTU=0; signed MAX=0. | Model only | MEDIUM | Passed
RV-05 | Model qualification | PACK(12345678, ABCDEF01); SEXT.B(00000080). | EF015678; FFFFFF80. | Model only | MEDIUM | Passed
RV-06 | Model qualification | CSR write-A/B with A=11223344, B=55667788; SUB(0, 1). | 11223344 / 55667788; FFFFFFFF. | Model only | MEDIUM | Passed
RV-07 | Model qualification | Legal NOP with valid_in=1, ap='0 and csr_ren_in=0; prior expected result is nonzero. | Reference prediction is result=00000000 and error=0. | Model only | MEDIUM | Passed