## Coverage
BMU COVERAGE PLAN
Only coverage information is kept here. Functional and cross coverage are in one table to avoid repetition.
Risk colors: | HIGH | MEDIUM | STANDARD
Coverage ID | Type | What it verifies | Target / Bins | Sample on | Main stimulus | Risk
C-OP | Functional | 21 approved legal operation/CSR mode identifiers. Unsupported GREV modes are tracked separately in C-GREV and do not count as legal-operation coverage. | 21 bins; operation/CSR tests. | Accepted legal request | All 18 operation sequences; csr_read; csr_write; mixed | STANDARD
C-A | Cross | 18 detailed operations x 8 disjoint A classes. | 144 reachable bins; V16 plus hole-fill stimulus. | Accepted legal request | All 18 operation sequences + mixed (explicit eight-class hole filling, including CPOP and SEXT.B) | STANDARD
C-LOG | Cross | 4 logic modes x 32 bit positions x 4 local A/B bit pairs. | 512 per-bit truth-table bins; OR/ORN/XOR/XNOR-03. | Legal accepted logic requests; loop over all 32 bit indices. | bmu_or_sequence; bmu_orn_sequence; bmu_xor_sequence; bmu_xnor_sequence | STANDARD
C-MODE | Functional | Documented runtime mode changes: OR/ORN, XOR/XNOR, SLT/SLTU and CSR-WA/WB, both directions. | Explicit mode-pair bins; no generic zbb enable assumption. | Accepted legal request | bmu_or_sequence; bmu_orn_sequence; bmu_xor_sequence; bmu_xnor_sequence; bmu_slt_sequence; bmu_sltu_sequence; bmu_csr_write_sequence; bmu_mixed_sequence | STANDARD
C-SH | Cross | SRL/SRA/ROR x 32 amounts x A[31]=0/1. | 192 bins; mandatory. | Accepted legal request | bmu_srl_sequence; bmu_sra_sequence; bmu_ror_sequence | MEDIUM
C-BIT | Cross | SRL/SRA/ROR x 32 onehot positions x 32 amounts. | 3,072 bins; deterministic 1,024-request sweeps per op. | Accepted legal request | bmu_srl_sequence; bmu_sra_sequence; bmu_ror_sequence | MEDIUM
C-INV | Cross | BINV index 0..31 x original A[index]=0/1. | 64 bins; BINV-01. | Accepted legal request | bmu_binv_sequence | STANDARD
C-UP | Cross | SRL/SRA/ROR/BINV/GREV x 32 low modes x 3 upper-B patterns. | 480 bins; GREV legal/unsupported classes kept separate. | Own predicates distinguish legal and unsupported GREV modes. | bmu_srl_sequence; bmu_sra_sequence; bmu_ror_sequence; bmu_binv_sequence; bmu_grev_sequence | MEDIUM
C-AR | Functional | SUB: borrow-chain position 0..31 and wrap boundaries. SH2ADD: top-A bits 00/01/10/11, B low 2=0..3 and carry endpoints 2..31. | Explicit directed scenario bins; no overflow-error assumption. | Accepted legal request | bmu_sh2add_sequence; bmu_sub_sequence | STANDARD
C-REL | Functional | SUB unsigned operand relation <, =, >; equality plus +/-1 scenarios. | 3 relation bins; SUB-01/02/05. | Accepted legal request | bmu_sub_sequence | STANDARD
C-CMP | Cross | SLT/SLTU/MAX x sign pair x operation-specific relation (<, =, >). | 8 reachable bins per op, 24 total. Exclude impossible sign/relation bins. | Accepted legal request | bmu_sltu_sequence; bmu_slt_sequence; bmu_max_sequence | MEDIUM
C-CTZ | Functional | Expected trailing-zero count 0..32; response value associated with the request. | 33 bins; CTZ-01..04. | Accepted legal request | bmu_ctz_sequence | MEDIUM
C-CTZ-X | Cross | Count 0..32 x A[31]; counts 0..30 both signs, 31 only MSB 1, 32 only MSB 0. | 64 reachable bins. Explicitly exclude two impossible bins. | Accepted legal request | bmu_ctz_sequence | STANDARD
C-POP | Functional | Expected population count 0..32. | 33 bins; POP-01. | Accepted legal request | bmu_cpop_sequence | STANDARD
C-POP-X | Cross | Weight 0..32 x A[31]; weights 1..31 both, 0 only MSB 0, 32 only MSB 1. | 64 reachable bins; POP-04. | Accepted legal request | bmu_cpop_sequence | STANDARD
C-BYTE | Functional | SEXT.B low byte 0..255. | 256 bins; SEXT-01. | Accepted legal request | bmu_sext_b_sequence | STANDARD
C-BYTE-X | Cross | Low byte 0..255 x three upper-A patterns. | 768 bins; SEXT-03. | Accepted legal request | bmu_sext_b_sequence | STANDARD
C-PACK | Cross | Six low-half classes in A x six in B; distinct source ordering. | 36 bins; PACK-02; additional asymmetric vector. | Accepted legal request | bmu_pack_sequence | STANDARD
C-PACK-B | Cross | Source lane A/B x bit index 0..15. | 32 propagation bins; PACK-03. | Accepted legal request | bmu_pack_sequence | STANDARD
C-GREV | Functional | All 32 low-five-bit modes; mode 24 legal, 31 isolated unsupported modes. | 32 bins; GREV-03. | Own predicates distinguish legal and unsupported GREV modes. | bmu_grev_sequence; bmu_errors_sequence | MEDIUM
C-GREV-B | Functional | Onehot position 0..31 with mode 24. | 32 bins; GREV-02. | Accepted legal request | bmu_grev_sequence | STANDARD
C-IGN | Functional | CTZ/CPOP/SEXT.B: B changes with relevant A unchanged. PACK: upper halves change while low halves fixed. | Directed relational checks; compare both outputs and independent oracle. | Accepted legal request | bmu_ctz_sequence; bmu_cpop_sequence; bmu_sext_b_sequence; bmu_pack_sequence | STANDARD
C-CSR / C-CSR-B | Cross | Three source paths x 8 selected-source classes; three paths x 32 onehot bits. | 24 +96 bins; CSR-01..06 plus hole filling. | Accepted legal request | bmu_csr_read_sequence; bmu_csr_write_sequence; bmu_mixed_sequence | MEDIUM
C-NEG | Cross | Recipe x single forbidden-field/CSR-conflict reason x valid_in 0/1; missing-required-control cases remain separate and blocked until defined. | Size derives from the Illegal Control Matrix. Known invalid controls must be exercised with valid_in=0 and 1. | Observed known-negative controls. error value is independent of valid_in; result_ff update/hold follows valid_in. Q2 only exact error-cycle alignment. | bmu_errors_sequence | HIGH
C-RST | Cross | 21 modes x valid_in 0/1 under reset; startup/midstream, reset-over-error and recovery flags. | 42 cross bins plus startup, midstream, reset-over-error and recovery observations. | Active reset edge | bmu_reset_sequence; bmu_mixed_sequence | HIGH
C-HOLD | Cross | 8 families x hold-length class 1, 2, 3-7, 8+. | 32 bins; execute TST-05 for all families. | Invalid cycles; family from last accepted request. | bmu_valid_in_sequence; bmu_mixed_sequence | MEDIUM
C-VALID | Cross | 8 families x valid transition 00, 01, 10, 11. | 32 bins; TST-06. | Every non-reset cycle | bmu_valid_in_sequence | MEDIUM
C-TR | Cross | All ordered 21 x 21 legal mode pairs on adjacent accepted cycles. | 441 bins; TST-07. Track conflict-recovery separately. | Adjacent accepted legal cycles | bmu_orn_sequence; bmu_xnor_sequence; bmu_srl_sequence; bmu_binv_sequence; bmu_sltu_sequence; bmu_sext_b_sequence; bmu_grev_sequence; bmu_csr_write_sequence; bmu_errors_sequence; bmu_mixed_sequence; bmu_smoke_sequence | STANDARD
C-REC | Functional | Known conflict reason x valid at conflict (0/1) x subsequent legal recovery observed. | Define per approved guard list; TST-08 supplies legal-conflict-legal runs. | Separate temporal coverage; do not use C-TR, whose history clears on conflict. error value is known for confirmed conflicts; Q2 only exact error-cycle alignment. | bmu_errors_sequence | STANDARD
C-LAT | Functional | Accepted request in cycle N x observed matching result in cycle N+1; include adjacent accepted requests and final drain. | All 21 legal modes represented; TST-02 is P0 alignment proof and TST-11 checks drain/accounting. | Sample accepted requests and compare only to the explicitly one-cycle-delayed expected-result queue. | bmu_smoke_sequence; all legal operation/CSR sequences; bmu_mixed_sequence | HIGH
C-ERR-V | Cross | Request legality class x valid_in 0/1 x observed error; include legal, known illegal control conflict, CSR conflict and unsupported GREV non-error class. | All defined reachable combinations. error must not be gated by valid_in. | Sample expected legality/error independently from result-register enable. Q2, if open, affects exact cycle alignment only. | bmu_errors_sequence; bmu_valid_in_sequence; bmu_reset_sequence; bmu_grev_sequence | HIGH
CODE | Code / Check | Line, branch, condition/expression and toggle coverage on actual DUT hierarchy. | Initial line/branch >=95% subject to approval; other holes reviewed. | Simulator instrumentation; per-build reports; justified exclusions only. | All runnable tests | STANDARD
ASSERT | Code / Check | Reset priority, hold, aligned update, scan setup and known controls. | Define properties for resolved behavior; review antecedent hits and vacuity. | Implement assertions/checkers. Result latency is confirmed; Q2 gates only error-cycle-specific properties. | reset; valid_in; smoke; errors; mixed | HIGH

## Sequences
BMU SEQUENCE PLAN
One row per sequence/test. The risk color is the highest risk level among scenarios owned by that sequence.
Risk colors: | HIGH | MEDIUM | STANDARD
Sequence | Test | Category | Responsibility / Legal Recipe | Scenarios | Risk | State
bmu_or_sequence | bmu_or_test | Operation | Control recipe: ap.lor=1. Expected value: A ¦ B. | 5 | STANDARD | Planned
bmu_orn_sequence | bmu_orn_test | Operation | Control recipe: ap.lor=1, ap.zbb=1. Expected value: A ¦ ~B. | 5 | STANDARD | Planned
bmu_xor_sequence | bmu_xor_test | Operation | Control recipe: ap.lxor=1. Expected value: A ^ B. | 5 | STANDARD | Planned
bmu_xnor_sequence | bmu_xnor_test | Operation | Control recipe: ap.lxor=1, ap.zbb=1. Expected value: ~(A ^ B). | 5 | STANDARD | Planned
bmu_srl_sequence | bmu_srl_test | Operation | Control recipe: ap.srl=1. Expected value: unsigned(A) >> s. | 5 | MEDIUM | Planned
bmu_sra_sequence | bmu_sra_test | Operation | Control recipe: ap.sra=1. Expected value: signed(A) >>> s. | 5 | MEDIUM | Planned
bmu_ror_sequence | bmu_ror_test | Operation | Control recipe: ap.ror=1. Expected value: rotate_right_32(A, s). | 5 | MEDIUM | Planned
bmu_binv_sequence | bmu_binv_test | Operation | Control recipe: ap.binv=1. Expected value: A ^ (32-bit one << s). | 5 | MEDIUM | Planned
bmu_sh2add_sequence | bmu_sh2add_test | Operation | Control recipe: ap.sh2add=1, ap.zba=1. Expected value: ((A << 2) + B) modulo 2^32. | 5 | STANDARD | Planned
bmu_sub_sequence | bmu_sub_test | Operation | Control recipe: ap.sub=1; ap.zba=0. Expected value: (A-B) modulo 2^32. | 5 | STANDARD | Planned
bmu_sltu_sequence | bmu_sltu_test | Operation | Control recipe: ap.slt=1, ap.sub=1, ap.unsign=1. Expected value: unsigned(A)<unsigned(B) ? 1 : 0. | 5 | MEDIUM | Planned
bmu_slt_sequence | bmu_slt_test | Operation | Control recipe: ap.slt=1, ap.sub=1; ap.unsign=0. Expected value: signed(A)<signed(B) ? 1 : 0. | 5 | MEDIUM | Planned
bmu_ctz_sequence | bmu_ctz_test | Operation | Control recipe: ap.ctz=1. Expected value: trailing-zero count of A, with CTZ(0)=32. | 5 | MEDIUM | Planned
bmu_cpop_sequence | bmu_cpop_test | Operation | Control recipe: ap.cpop=1. Expected value: sum of all 32 operand bits. | 5 | STANDARD | Planned
bmu_sext_b_sequence | bmu_sext_b_test | Operation | Control recipe: ap.siext_b=1. Expected value: sign_extend_32(A[7:0]). | 5 | STANDARD | Planned
bmu_max_sequence | bmu_max_test | Operation | Control recipe: ap.max=1, ap.sub=1; ap.unsign=0. Expected value: larger signed operand. | 5 | MEDIUM | Planned
bmu_pack_sequence | bmu_pack_test | Operation | Control recipe: ap.pack=1. Expected value: {B[15:0], A[15:0]}. | 5 | STANDARD | Planned
bmu_grev_sequence | bmu_grev_test | Operation | Control recipe: ap.grev=1; B[4:0]=24 for REV8. Expected value: {A[7:0], A[15:8], A[23:16], A[31:24]}. | 5 | MEDIUM | Planned
bmu_csr_read_sequence | bmu_csr_read_test | Shared / smoke | CSR read path; shared CSR-06 bit sweep. | 3 | MEDIUM | Planned
bmu_csr_write_sequence | bmu_csr_write_test | Shared / smoke | CSR write-A/write-B paths; execute write portions of shared CSR-06. | 3 | MEDIUM | Planned
bmu_errors_sequence | bmu_errors_test | Shared / smoke | Reviewed invalid controls, CSR conflicts, error/recovery and negative campaigns. | 14 | HIGH | Planned
bmu_reset_sequence | bmu_reset_test | Shared / smoke | Synchronous reset, priority and mid-traffic recovery. | 4 | HIGH | Planned
bmu_valid_in_sequence | bmu_valid_in_test | Shared / smoke | Hold lengths, valid transitions, repeated updates and CSR hold. | 4 | HIGH | Planned
bmu_mixed_sequence | bmu_mixed_test | Shared / smoke | Adjacent mode pairs, CSR path transitions and shared random campaigns. | 6 | HIGH | Planned
bmu_smoke_sequence | bmu_smoke_test | Shared / smoke | Bring-up, three checked updates, alignment, drain and scan setup. | 3 | HIGH | Skeleton only
Model qualification (no DUT sequence) | bmu_reference_model_unit_test | Support | Known-answer checks for the independent reference model before DUT sign-off. | 6 | MEDIUM | Planned

## Scenarios
BMU SCENARIO PLAN
Scenarios are grouped under their owning sequence. Sequence/test names appear once per group, not on every row.
Risk colors: | HIGH | MEDIUM | STANDARD
bmu_or_sequence ¦ bmu_or_test ¦ 5 scenarios ¦ Group risk: STANDARD
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Blocker
OR-01 | Operation | All 256 ordered V16 x V16 pairs. | Compare complete 32-bit OR result. | C-OP, C-A | STANDARD | Planned
OR-02 | Operation | H32[k] against 0, same bit, and next bit; all k. | Selected bits combine; no bit disappears. | C-LOG | STANDARD | Planned
OR-03 | Operation | Per bit k, construct local (A[k], B[k])=00, 01, 10, 11; 128 requests. | Truth table: 0, 1, 1, 1 at the selected bit; check full word. | C-LOG | STANDARD | Planned
OR-04 | Operation | Alternate B=0 and FFFFFFFF for each V16 A. | F=A, then F=FFFFFFFF. | C-A | STANDARD | Planned
OR-05 | Operation | Repeat A=0, B=12345678 with zbb=0/1. | OR=12345678; ORN=EDCBA987. | C-MODE | STANDARD | Planned
bmu_orn_sequence ¦ bmu_orn_test ¦ 5 scenarios ¦ Group risk: STANDARD
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Blocker
ORN-01 | Operation | All 256 ordered V16 x V16 pairs. | Compare full 32-bit OR-with-inverted-B. | C-OP, C-A | STANDARD | Planned
ORN-02 | Operation | B=0/FFFFFFFF for every V16 A. | F=FFFFFFFF / A respectively. | C-A | STANDARD | Planned
ORN-03 | Operation | Per bit k, local pairs 00, 01, 10, 11; 128 requests. | Selected-bit truth table: 1, 0, 1, 1. | C-LOG | STANDARD | Planned
ORN-04 | Operation | A=0; B sweeps H32 and L32. | F=~B; exercise both bit polarities. | C-LOG | STANDARD | Planned
ORN-05 | Operation | Consecutive ORN/OR on identical asymmetric operands. | Only documented zbb mode changes; align results. | C-MODE, C-TR | STANDARD | Planned
bmu_xor_sequence ¦ bmu_xor_test ¦ 5 scenarios ¦ Group risk: STANDARD
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Blocker
XOR-01 | Operation | All 256 ordered V16 x V16 pairs. | Compare full 32-bit XOR. | C-OP, C-A | STANDARD | Planned
XOR-02 | Operation | B=A and B=~A for each V16 A. | F=0 and FFFFFFFF respectively. | C-A | STANDARD | Planned
XOR-03 | Operation | Per bit k, local pairs 00, 01, 10, 11; 128 requests. | Selected-bit truth table: 0, 1, 1, 0. | C-LOG | STANDARD | Planned
XOR-04 | Operation | A sweeps H32/L32; B=0 then FFFFFFFF. | F=A then ~A. | C-LOG | STANDARD | Planned
XOR-05 | Operation | Swap A/B in each V16 pair. | Same F, also checked independently against A ^ B. | C-A | STANDARD | Planned
bmu_xnor_sequence ¦ bmu_xnor_test ¦ 5 scenarios ¦ Group risk: STANDARD
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Blocker
XNOR-01 | Operation | All 256 ordered V16 x V16 pairs. | Compare full 32-bit XNOR. | C-OP, C-A | STANDARD | Planned
XNOR-02 | Operation | B=A and B=~A for each V16 A. | F=FFFFFFFF and 0 respectively. | C-A | STANDARD | Planned
XNOR-03 | Operation | Per bit k, local pairs 00, 01, 10, 11; 128 requests. | Selected-bit truth table: 1, 0, 0, 1. | C-LOG | STANDARD | Planned
XNOR-04 | Operation | A sweeps H32/L32; B=0 then FFFFFFFF. | F=~A then A. | C-LOG | STANDARD | Planned
XNOR-05 | Operation | Alternate XOR/XNOR with fixed A=AAAAAAAA, B=55555555. | FFFFFFFF then 00000000; correct mode/cycle. | C-MODE, C-TR | STANDARD | Planned
bmu_srl_sequence ¦ bmu_srl_test ¦ 5 scenarios ¦ Group risk: MEDIUM
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Blocker
SRL-01 | Operation | V16 x S32: 512 requests. | Zero-fill logical shift; s=0 preserves A. | C-SH, C-A | MEDIUM | Planned
SRL-02 | Operation | H32[k] x S32: 1,024 requests. | Bit remains at k-s if k>=s; otherwise F=0. | C-BIT | MEDIUM | Planned
SRL-03 | Operation | A=80000001; s=0, 1, 30, 31. | 80000001, 40000000, 00000002, 00000001. | C-SH | MEDIUM | Planned
SRL-04 | Operation | For each s, repeat three B[31:5] patterns and both A sign bits. | Only B[4:0] affects F. | C-UP | MEDIUM | Planned
SRL-05 | Operation | Alternate SRL/SRA with A=80000000, s=1. | 40000000 / C0000000 respectively. | C-MODE, C-TR | MEDIUM | Planned
bmu_sra_sequence ¦ bmu_sra_test ¦ 5 scenarios ¦ Group risk: MEDIUM
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Blocker
SRA-01 | Operation | V16 x S32: 512 requests. | Sign-filled arithmetic shift. | C-SH, C-A | MEDIUM | Planned
SRA-02 | Operation | H32[k] x S32; include negative onehot at k=31. | Reference uses signed 32-bit A, not an unsigned cast. | C-BIT | MEDIUM | Planned
SRA-03 | Operation | A=80000000 / 7FFFFFFF; s=31. | FFFFFFFF / 00000000. | C-SH | MEDIUM | Planned
SRA-04 | Operation | A=FFFFFFFF; all s; repeat A=80000001 at s=0/1/31. | FFFFFFFF throughout; then 80000001/C0000000/FFFFFFFF. | C-SH | MEDIUM | Planned
SRA-05 | Operation | Every s x both sign bits x three upper-B patterns. | Same result for matching A and s despite B upper changes. | C-UP | MEDIUM | Planned
bmu_ror_sequence ¦ bmu_ror_test ¦ 5 scenarios ¦ Group risk: MEDIUM
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Blocker
ROR-01 | Operation | V16 x S32: 512 requests. | s=0 returns A; implement zero-shift case explicitly. | C-SH, C-A | MEDIUM | Planned
ROR-02 | Operation | H32[k] x S32: 1,024 requests. | Exactly one bit at (k-s) modulo 32. | C-BIT | MEDIUM | Planned
ROR-03 | Operation | A=80000001; s=1/31. | C0000000 / 00000003. | C-SH | MEDIUM | Planned
ROR-04 | Operation | Each s with three B upper patterns; A has distinct end bits. | B upper bits ignored; wrapped bits preserved. | C-UP | MEDIUM | Planned
ROR-05 | Operation | A=0/FFFFFFFF/55555555/AAAAAAAA; all s. | Zero/ones invariant; alternating patterns exchange on odd s. | C-SH | MEDIUM | Planned
bmu_binv_sequence ¦ bmu_binv_test ¦ 5 scenarios ¦ Group risk: MEDIUM
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Blocker
BINV-01 | Operation | All 32 indices with target A[s]=0 and 1; 64 requests minimum. | Only target bit toggles. | C-INV | MEDIUM | Planned
BINV-02 | Operation | V16 x S32: 512 requests. | Compare all bits; all non-target bits unchanged. | C-INV, C-A | MEDIUM | Planned
BINV-03 | Operation | A=0, s=31; A=FFFFFFFF, s=0. | 80000000; FFFFFFFE. | C-INV | MEDIUM | Planned
BINV-04 | Operation | For each index, repeat three B upper patterns. | Same F for same A and s. | C-UP | MEDIUM | Planned
BINV-05 | Operation | Invert same bit twice; software-feed the first expected F as next A. | Second result restores original A; both results checked independently. | C-INV, C-TR | MEDIUM | Planned
bmu_sh2add_sequence ¦ bmu_sh2add_test ¦ 5 scenarios ¦ Group risk: STANDARD
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Blocker
SH2-01 | Operation | All 256 ordered V16 x V16 pairs. | 32-bit shifted A plus full 32-bit B. | C-OP, C-A | STANDARD | Planned
SH2-02 | Operation | A=1; B=0/1/2/3. | F=4/5/6/7; preserve B low bits. | C-AR | STANDARD | Planned
SH2-03 | Operation | Fix A[29:0]=1; sweep A[31:30]=00/01/10/11; B=3. | F=7 for all four; top A bits shift out. | C-AR | STANDARD | Planned
SH2-04 | Operation | A=3FFFFFFF, B=4; A=FFFFFFFF, B=FFFFFFFF. | 00000000; FFFFFFFB; wrap is not an error. | C-AR | STANDARD | Planned
SH2-05 | Operation | For k=2..31: A=(1<<(k-2))-1, B=4. | F=1<<k; long carry chains; also A=3FFFFFFF, B=4 wraps. | C-AR | STANDARD | Planned
bmu_sub_sequence ¦ bmu_sub_test ¦ 5 scenarios ¦ Group risk: STANDARD
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Blocker
SUB-01 | Operation | All 256 ordered V16 x V16 pairs. | Full 32-bit subtraction. | C-OP, C-A | STANDARD | Planned
SUB-02 | Operation | A=B for every V16 value. | F=0. | C-REL | STANDARD | Planned
SUB-03 | Operation | A=0, B=1; A=80000000, B=1; A=7FFFFFFF, B=FFFFFFFF. | FFFFFFFF; 7FFFFFFF; 80000000. | C-AR | STANDARD | Planned
SUB-04 | Operation | A=H32[k], B=1 for k=0..31. | F=(1<<k)-1; sweep borrow-chain lengths. | C-AR | STANDARD | Planned
SUB-05 | Operation | A=B-1/B/B+1 for B in 1, 2, 7FFFFFFF, 80000000, FFFFFFFE. | FFFFFFFF/0/1 respectively; no comparison shortcut. | C-REL | STANDARD | Planned
bmu_sltu_sequence ¦ bmu_sltu_test ¦ 5 scenarios ¦ Group risk: MEDIUM
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Blocker
SLTU-01 | Operation | All 256 ordered V16 x V16 pairs. | Only 00000000 or 00000001. | C-CMP, C-A | MEDIUM | Planned
SLTU-02 | Operation | Equal A/B for V16; adjacent values around 0, 7FFFFFFF, 80000000, FFFFFFFF. | Equality gives 0; compare unsigned order. | C-CMP | MEDIUM | Planned
SLTU-03 | Operation | A=FFFFFFFF, B=0; A=80000000, B=7FFFFFFF; swap each pair. | 0, 0; swapped results both 1. | C-CMP | MEDIUM | Planned
SLTU-04 | Operation | Construct all reachable sign-bit-pair x unsigned-relation bins. | Same signs: <, =, >; 0/1 forces <; 1/0 forces >. | C-CMP | MEDIUM | Planned
SLTU-05 | Operation | Same A=FFFFFFFF, B=0; alternate unsign=1/0. | SLTU=0; SLT=1. | C-MODE, C-TR | MEDIUM | Planned
bmu_slt_sequence ¦ bmu_slt_test ¦ 5 scenarios ¦ Group risk: MEDIUM
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Blocker
SLT-01 | Operation | All 256 ordered V16 x V16 pairs. | Sign-correct comparison; upper 31 result bits always 0. | C-CMP, C-A | MEDIUM | Planned
SLT-02 | Operation | Equal negative/positive values; adjacent signed values near -1, 0 and limits. | Equality=0; signed relation drives result. | C-CMP | MEDIUM | Planned
SLT-03 | Operation | A=80000000, B=7FFFFFFF and reverse. | 1 then 0, despite subtraction overflow risk. | C-CMP | MEDIUM | Planned
SLT-04 | Operation | Construct all reachable sign-bit-pair x signed-relation bins. | Same signs: <, =, >; 0/1 forces >; 1/0 forces <. | C-CMP | MEDIUM | Planned
SLT-05 | Operation | A=FFFFFFFE, B=FFFFFFFF; swap pair. | 1 then 0; compare two negative numbers. | C-CMP | MEDIUM | Planned
bmu_ctz_sequence ¦ bmu_ctz_test ¦ 5 scenarios ¦ Group risk: MEDIUM
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Blocker
CTZ-01 | Operation | A=0/FFFFFFFF/1. | 32 / 0 / 0 decimal. | C-CTZ | MEDIUM | Planned
CTZ-02 | Operation | All H32[k], k=0..31. | Result k; every nonzero count class. | C-CTZ | STANDARD | Planned
CTZ-03 | Operation | For k=0..30, keep A[k]=1 and all lower bits 0; randomize higher bits, both MSB values. | Result stays k. For k=31 only A=80000000 is possible. | C-CTZ-X | STANDARD | Planned
CTZ-04 | Operation | V16 plus values 00010000, 00008000, 01000000, 00800000. | Counts across byte/halfword boundaries. | C-CTZ, C-A | STANDARD | Planned
CTZ-05 | Operation | For each k and zero case, vary unused B across V16. | Result independent of B; 33 x 16 requests. | C-IGN | STANDARD | Planned
bmu_cpop_sequence ¦ bmu_cpop_test ¦ 5 scenarios ¦ Group risk: STANDARD
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Blocker
POP-01 | Operation | Generate each weight w=0..32 with low-end and high-end packed ones. | F=w; every population count is explicitly reached. | C-POP | STANDARD | Planned
POP-02 | Operation | H32 and L32; all 64 words. | 1 for onehot; 31 for onecold, including MSB. | C-POP-X | STANDARD | Planned
POP-03 | Operation | A=FFFF0000/0000FFFF/FFFFFFFF/AAAAAAAA. | 16/16/32/16. | C-POP | STANDARD | Planned
POP-04 | Operation | For w=1..31, generate both A[31]=0/1 at weight w; w=0 and 32 each have one legal MSB. | Same count w across all reachable MSB combinations. | C-POP-X | STANDARD | Planned
POP-05 | Operation | For every w, permute set-bit positions and vary B across V16. | Position and B changes do not alter F=w. | C-IGN, C-POP | STANDARD | Planned
bmu_sext_b_sequence ¦ bmu_sext_b_test ¦ 5 scenarios ¦ Group risk: STANDARD
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Blocker
SEXT-01 | Operation | BYTE256 with upper A=0. | All 256 low-byte values; sign-extend bit 7. | C-BYTE | STANDARD | Planned
SEXT-02 | Operation | Low byte 00, 01, 7F, 80, FE, FF. | 00000000, 00000001, 0000007F, FFFFFF80, FFFFFFFE, FFFFFFFF. | C-BYTE | STANDARD | Planned
SEXT-03 | Operation | BYTE256 x upper-A patterns 0, FFFFFF, AAAAAA. | Same F for same low byte; 768 requests. | C-BYTE-X | STANDARD | Planned
SEXT-04 | Operation | Low bytes 7F and 80 with B across V16. | F=0000007F / FFFFFF80 independent of B. | C-IGN | STANDARD | Planned
SEXT-05 | Operation | A=8000007F then 00000080 on adjacent valid cycles. | Sign comes from bit 7, not bit 31. | C-BYTE-X, C-TR | STANDARD | Planned
bmu_max_sequence ¦ bmu_max_test ¦ 5 scenarios ¦ Group risk: MEDIUM
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Blocker
MAX-01 | Operation | All 256 ordered V16 x V16 pairs. | Full selected 32-bit operand, not a Boolean. | C-CMP, C-A | MEDIUM | Planned
MAX-02 | Operation | A=B for V16 values. | Same input value; no unobservable tie-source requirement. | C-CMP | MEDIUM | Planned
MAX-03 | Operation | A=80000000, B=7FFFFFFF; A=FFFFFFFF, B=0. | 7FFFFFFF; 00000000. | C-CMP | MEDIUM | Planned
MAX-04 | Operation | Both negatives: A=FFFFFFFE, B=FFFFFFFF; swap. | FFFFFFFF in both orders. | C-CMP | MEDIUM | Planned
MAX-05 | Operation | Construct every reachable sign-pair x signed-relation bin. | Correct signed selection for <, =, >; unsigned mode remains blocked Q6. | C-CMP | MEDIUM | Planned
bmu_pack_sequence ¦ bmu_pack_test ¦ 5 scenarios ¦ Group risk: STANDARD
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Blocker
PACK-01 | Operation | A=12345678, B=ABCDEF01; then swap. | EF015678; 5678EF01. | C-PACK | STANDARD | Planned
PACK-02 | Operation | Low-half patterns 0000, FFFF, 0001, 8000, 5555, AAAA; all 36 ordered pairs. | Exact halfword concatenation. | C-PACK | STANDARD | Planned
PACK-03 | Operation | Walk a bit through A[15:0] then B[15:0], other operand zero; 32 requests. | Output bits 0..15 /16..31 respectively. | C-PACK-B | STANDARD | Planned
PACK-04 | Operation | Fixed low halves 1234/ABCD; each upper half sweeps 0, FFFF, AAAA (9 pairs). | F=ABCD1234 unchanged. | C-IGN | STANDARD | Planned
PACK-05 | Operation | V16 x V16; include A=FFFF0000, B=FFFF0000. | Model concatenation; example gives zero. | C-A, C-PACK | STANDARD | Planned
bmu_grev_sequence ¦ bmu_grev_test ¦ 5 scenarios ¦ Group risk: MEDIUM
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Blocker
GREV-01 | Operation | A=12345678/80010204/00000001; mode 24. | 78563412/04020180/01000000. | C-GREV | MEDIUM | Planned
GREV-02 | Operation | H32 and L32; mode 24. | Swap byte positions; preserve bit position inside each byte. | C-GREV-B | MEDIUM | Planned
GREV-03 | Operation | All 32 mode values with distinct-byte A. | Mode24 reverses; isolated other modes give F=0, error=0. | C-GREV | MEDIUM | Planned
GREV-04 | Operation | Each mode x B upper patterns zero, all-one, alternating. | Only low 5 bits select mode; 96 requests minimum. | C-UP | MEDIUM | Planned
GREV-05 | Operation | Reverse twice using expected first F as second A; V16. | Restore original A; independently check both values. | C-TR, C-A | MEDIUM | Planned
bmu_csr_read_sequence ¦ bmu_csr_read_test ¦ 3 scenarios ¦ Group risk: MEDIUM
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Blocker
CSR-01 | CSR | Read: ap=0, csr_ren_in=1; csr_rddata_in sweeps V16. | F=csr_rddata_in; isolated read error=0 per baseline. | C-CSR | MEDIUM | Planned
CSR-02 | CSR | Read: each V16 read-data value; A/B selected to differ from it. | No leakage from A or B. | C-CSR | MEDIUM | Planned
CSR-06 | CSR | For each path, H32/L32 sweeps on selected source; vary unused sources. | All selected-source bits propagate correctly. | C-CSR-B | MEDIUM | Planned
bmu_csr_write_sequence ¦ bmu_csr_write_test ¦ 3 scenarios ¦ Group risk: MEDIUM
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Blocker
CSR-03 | CSR | Write-A: csr_write=1, csr_imm=0, csr_ren_in=0; V16 A. | F=A, not B or read-data. | C-CSR | MEDIUM | Planned
CSR-04 | CSR | Write-B: csr_write=1, csr_imm=1, csr_ren_in=0; V16 B. | F=B; no truncation or unapproved immediate extraction. | C-CSR | MEDIUM | Planned
CSR-08 | CSR | Change csr_imm every cycle under isolated writes and distinct A/B. | Each update selects that cycle’s source; no stale mode. | C-TR, C-CSR | MEDIUM | Planned
bmu_errors_sequence ¦ bmu_errors_test ¦ 14 scenarios ¦ Group risk: HIGH
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Blocker
CSR-09 | CSR | csr_ren_in=1 and csr_write=1, both csr_imm values. | Data priority and error undefined pending Q4. | Blocked Q4 | MEDIUM | Blocked | Q4
CSR-10 | CSR | csr_imm=1 with csr_write=0; test read inactive/active. | Ignored versus invalid behavior pending Q4. | Blocked Q4 | MEDIUM | Blocked | Q4
NEG-01 | Control legality | For every documented BMU recipe whose guard requires unrelated ap.* fields to be 0, assert one forbidden ap.* field at a time with csr_ren_in=0. Run each mutation with valid_in=0 and 1. Detailed rows are in Illegal Control Matrix. | Each single forbidden-field conflict is sufficient: error=1. If valid_in=1, invalid F=0 is captured at N+1; if valid_in=0, result_ff holds its previous value. | C-NEG, C-ERR-V | HIGH | Planned
NEG-02 | Control legality | For every documented operation requiring csr_ren_in=0, assert csr_ren_in=1 while all unrelated ap.* fields remain clear. Run with valid_in=0 and 1. Detailed rows are in Illegal Control Matrix. | CSR conflict alone is sufficient: error=1; a second forbidden ap field is not required. valid_in controls result_ff update/hold only, not error. | C-NEG, C-ERR-V | HIGH | Planned
NEG-03 | Control legality | OR/ORN and XOR/XNOR with documented zbb qualifier only. | Legal mode switch, not a conflict. | C-MODE | HIGH | Planned
NEG-04 | Control legality | sh2add=1, zba=0; compare with legal zba=1. | Invalid: F=0, error=1; legal: SH2ADD formula. | C-NEG | HIGH | Planned
NEG-05 | Control legality | Isolated sub=1 with zba=1; compare zba=0. | Invalid: F=0, error=1; legal: SUB formula. | C-NEG | HIGH | Planned
NEG-06 | Control legality | grev=1, mode 24; add each forbidden field, then CSR conflict separately. | At legal REV8 mode (b_in[4:0]=24), a forbidden control or CSR conflict gives error=1. With valid_in=1 invalid F=0 is captured at N+1; with valid_in=0 result_ff holds. | C-NEG, C-ERR-V | HIGH | Planned
NEG-07 | Control legality | grev=1, mode!=24; all other controls clear. | With GREV selected, b_in[4:0]!=24 and no control conflict: F=0 and error=0. valid_in=1 may capture 0 at N+1; valid_in=0 holds the previous result. | C-GREV, C-ERR-V | MEDIUM | Planned
NEG-08 | Control legality | Missing required qualifier/control cases only (for example SLT/SLTU/MAX without the required sub control) where the supplied sources do not explicitly define the error/result behavior. Extra-field mutations are handled by NEG-01. | No expected result/error is assigned until the missing-required-control behavior is explicitly approved. | Guard review | STANDARD | Blocked | Open
NEG-09 | Control legality | Combine two forbidden controls only after single mutations are qualified. | Use approved combined guard; unknown interactions stay blocked. | Guard review | STANDARD | Blocked | Guard
NEG-10 | Control legality | valid=1, ap=0, csr_ren_in=0; nonzero prior result. | Result and error pending Q5. | Blocked Q5 | STANDARD | Blocked | Q5
RND-02 | Campaign | After the confirmed single-conflict guard matrix is mapped to actual ap fields: 10 seeds x 2,000 known-negative trials; split valid_in=0/1 and preserve failing seeds. | 20,000 trials; error independent of valid_in; result update/hold follows valid_in and confirmed one-cycle result timing. | C-NEG, C-ERR-V | HIGH | Planned
TST-08 | Timing / setup | Legal -> known conflict -> legal, with valid pattern 111 and 101. | Conflict zeros result only in valid case; later legal update recovers. | C-NEG, C-TR | HIGH | Planned
bmu_reset_sequence ¦ bmu_reset_test ¦ 4 scenarios ¦ Group risk: HIGH
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Blocker
TST-01 | Timing / setup | Reset at startup, after nonzero results, and while a known error-producing control combination remains asserted. Apply rst_l=0 across an active edge with valid_in=0 and 1 cases. | At the active synchronous reset edge result_ff=0 and error=0. After release, checking restarts from reset state and later legal traffic updates normally. | C-RST, C-ERR-V | HIGH | Planned
TST-03 | Timing / setup | All 21 legal modes x valid=0/1 while reset is active; 42 cases. | Reset dominates result update for every mode. | C-RST | HIGH | Planned
TST-04 | Timing / setup | Change rst_l between rising edges, with stable nonzero result; then hold across next edge. | Synchronous result changes at active reset edge, not at reset assertion alone. | C-RST | HIGH | Planned
TST-09 | Timing / setup | Reset during traffic; deassert before next active edge; send fresh legal requests. | Discard reset-invalidated predictions; first post-reset update checked. | C-RST | HIGH | Planned
bmu_valid_in_sequence ¦ bmu_valid_in_test ¦ 4 scenarios ¦ Group risk: HIGH
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Blocker
CSR-07 | CSR | Each path with valid=0 after a nonzero registered result. | result_ff holds; error follows independent contract. | C-HOLD | MEDIUM | Planned
TST-05 | Timing / setup | Known nonzero result; idle lengths 1, 2, 3, 7, 16 while A/B/control inputs change. | No result update while valid_in=0; result_ff holds the prior value even as operands/controls change. error checking remains active and is not gated by valid_in. | C-HOLD, C-ERR-V | HIGH | Planned
TST-06 | Timing / setup | Every valid transition 00/01/10/11 for each of 8 operation families. | Hold/update behavior follows captured valid, not sequence intention. | C-VALID | MEDIUM | Planned
TST-10 | Timing / setup | Repeat same legal request for 8 valid cycles, then change only operands. | Every valid cycle counts as an update; identical results do not mean missing requests. | C-VALID | MEDIUM | Planned
bmu_mixed_sequence ¦ bmu_mixed_test ¦ 6 scenarios ¦ Group risk: HIGH
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Blocker
CSR-05 | CSR | A=11223344, B=55667788, read-data=99AABBCC; alternate the three isolated paths. | 11223344 /55667788 /99AABBCC in the requested order. | C-TR, C-CSR | MEDIUM | Planned
RND-01 | Campaign | 10 fixed seeds; per seed, 500 accepted requests per legal mode (21 modes). | 105,000 legal requests total; all expected results compared. | C-OP, C-A | MEDIUM | Planned
RND-03 | Campaign | 10 seeds x 2,000 cycles: legal traffic, hold bursts, reset interruptions. | 20,000 cycles; accepted updates, holds and resets accounted separately. | C-RST, C-HOLD | HIGH | Planned
RND-04 | Campaign | Bias stimulus toward each uncovered reachable functional bin. | Stop targeted campaign when its named holes close; record seeds. | Any open C-* | MEDIUM | Planned
RND-05 | Campaign | 5 additional seeds after fixes and closure; same approved legal campaign. | No regressions; seeds differ from initial discovery set. | Stability | MEDIUM | Planned
TST-07 | Timing / setup | All ordered pairs of 21 legal mode IDs; execute each pair back-to-back. | 441 transition bins; at least 882 directed requests before extra boundary samples. | C-TR | STANDARD | Planned
bmu_smoke_sequence ¦ bmu_smoke_test ¦ 3 scenarios ¦ Group risk: HIGH
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Blocker
TST-02 | Timing / setup | Three distinct operations/outputs on adjacent valid cycles, then idle drain. | Each accepted request in cycle N is checked against result_ff in cycle N+1. Exactly three aligned result checks occur, with no dropped last response or extra latency. | C-LAT, C-TR | HIGH | Planned
TST-11 | Timing / setup | End traffic explicitly with valid=0 and drain aligned comparison pipeline. | No unintended repeated last request; pending entries zero or explained. | C-LAT, Accounting | HIGH | Planned
TST-12 | Timing / setup | Keep scan_mode=0 through startup, reset, random traffic and idle. | Violation is a TB setup failure; scan-chain behavior excluded. | Setup | STANDARD | Planned
Model qualification (no DUT sequence) ¦ bmu_reference_model_unit_test (support) ¦ 6 scenarios ¦ Group risk: MEDIUM
Scenario ID | Area | Stimulus / Sweep | Expected Behavior | Coverage | Risk | Status | Blocker
RV-01 | Model qualification | CPOP(FFFF0000), CPOP(80000000), CPOP(FFFFFFFF). | 16, 1, 32 respectively. | Model only | MEDIUM | Planned
RV-02 | Model qualification | CTZ(0), CTZ(1), CTZ(00000008), CTZ(80000000). | 32, 0, 3, 31 respectively. | Model only | MEDIUM | Planned
RV-03 | Model qualification | REV8(12345678), mode=24; ROR(80000001, 1). | 78563412; C0000000. | Model only | MEDIUM | Planned
RV-04 | Model qualification | SLT/SLTU with A=FFFFFFFF, B=0; MAX with same operands. | SLT=1; SLTU=0; signed MAX=0. | Model only | MEDIUM | Planned
RV-05 | Model qualification | PACK(12345678, ABCDEF01); SEXT.B(00000080). | EF015678; FFFFFF80. | Model only | MEDIUM | Planned
RV-06 | Model qualification | CSR write-A/B with A=11223344, B=55667788; SUB(0, 1). | 11223344 / 55667788; FFFFFFFF. | Model only | MEDIUM | Planned